## Tabelle1
		Legend				Legend
		not started				Done this week	not started
		started				Next steps	started
		done					done

Writing					Implementation
Date	Milestone	Progress	Comments		Date	Milestone	Progress	Comments
	Abstract				15-May	Install pysgpp & virtual box
29-May	Introduction to SG				15-May	Pysgpp tutorial
29-May	Derive SG Formula		Needs to be fleshed out with description, just a rough derivation sketch so far		5-Jun	File parser
	Link regular SG to timeseries prediction				12-Jun	Rescale data to sg interval		Rescaled samples and values individually, need to combine (and use same scaling for test data)
	Comparable procedures				12-Jun	Be able to get results for an arbitrary timeseries with a regression
24-Apr	Introduction to financial data & the stock market (what, why, how does it work)				12-Jun	Calculate Error with RMSE
24-Apr	Different kinds of financial data, different kinds of markets (bullish/bearish, volatile/stable)				12-Jun	Allow selection of data load method (function / file)
24-Apr	Source of financial data				12-Jun	Build regression learner based on passed parameters		Could add additional options later
24-Apr	Typical analysis of financial data				12-Jun	Give regression learner specified training data
	Prediction Pseudo Code				12-Jun	Test regression learner with specified testing data
	Pre-Processing (link with financial data analysis)				12-Jun	Allow selection of error calculation method & calculate training and test error
	Compare results to reference paper & visualize				19-Jun	Test results for the Henon map		RMSE better for level 3 parameters, worse for level 6 parameters, significantly worse for level 7 parameters
	Compare results with actual financial data & visualize (For each (supposed) improvement separately)				06.07 / 07.07	Check why Henon map results for higher levels don’t get more accurate
						Add preconditioning
						Add adaptivity
						Test results for Jump Map, ANN & CI Forecasting Competition 2006/2007
					19-Jun	Testing system
					19-Jun	Financial Data pipeline
						Test non-adaptive system for all markets combined
						Test non-adaptive system for different markets
						Test adaptive system for all markets combined
						Test adaptive system for different markets
						Pre Processing of finance data
						Test adaptive system w/ preprocessing for all markets combined
						Test adaptive system w/ preprocessing for different markets
						Other improvements