## Tabelle1
		Legend				Legend
		not started				Done this week	not started
		started					started
		done					done

Writing					Implementation
Date	Milestone	Progress	Comments		Date	Milestone	Progress	Comments
	Abstract				15-May	Install pysgpp & virtual box
29-May	Introduction to SG				15-May	Pysgpp tutorial
29-May	Derive SG Formula		Needs to be fleshed out with description, just a rough derivation sketch so far		5-Jun	File parser
	Link regular SG to timeseries prediction				12-Jun	Rescale data to sg interval
	Comparable procedures		Reference paper for Deep Learning in a similar use case		12-Jun	Be able to get results for an arbitrary timeseries with a regression
28.08.	Introduction to financial data & the stock market (what, why, how does it work)		First draft, need to turn into proper English now		12-Jun	Calculate Error with RMSE
28.08.	Different kinds of financial data, different kinds of markets (bullish/bearish, volatile/stable)		First draft, need to turn into proper English now		12-Jun	Allow selection of data load method (function / file)
28.08.	Source of financial data		First draft, need to turn into proper English now		12-Jun	Build regression learner based on passed parameters
28.08.	Typical analysis of financial data		First draft, need to turn into proper English now		12-Jun	Give regression learner specified training data
	Prediction Pseudo Code				12-Jun	Test regression learner with specified testing data
	Pre-Processing (link with financial data analysis)				12-Jun	Allow selection of error calculation method & calculate training and test error
	Compare results to reference paper & visualize				19-Jun	Test results for the Henon map
	Compare results with actual financial data & visualize (For each (supposed) improvement separately)				12.07	Check why Henon map results for higher levels don’t get more accurate
25.07.	Added proposal for detailed outline				12.07	Add preconditioning
					25.07.	Add adaptivity
					28.08.	Test results for Jump Map, ANN & CI Forecasting Competition 2006/2007
					28.08.	Testing system
					28.08.	Financial Data pipeline
					28.08.	Test non-adaptive system for SP500
					28.08.	Test non-adaptive system for Crypto Currency
					28.08.	Test adaptive system for all markets combined
					28.08.	Test adaptive system for different markets
					25.07.	Pre Processing of finance data		Add suitable prediction market identification (test for different market types, see if prediction is more applicable to some – if yes -> add identification as preprocessing. If no →no need for identification)
						Test adaptive system w/ preprocessing for all markets combined
						Test adaptive system w/ preprocessing for different markets
						Other improvements
					18.07.	Visualization
					25.07.	Added dimensionality estimation with Grassberger algorithm
					07.08.	Downloaded over 2000 company stocks & calculated embedding dimension. Stored both in csv files