## Tabelle1
		Legend				Legend
		not started				Done this week	not started
		started				Next steps	started
		done					done

Writing					Implementation
Date	Milestone	Progress	Comments		Date	Milestone	Progress	Comments
	Abstract				15-May	Install pysgpp & virtual box
29-May	Introduction to SG				15-May	Pysgpp tutorial
29-May	Derive SG Formula		Needs to be fleshed out with description, just a rough derivation sketch so far		5-Jun	File parser
	Link regular SG to timeseries prediction				12-Jun	Rescale data to sg interval		Rescaled samples and values individually, need to combine (and use same scaling for test data)
	Comparable procedures				12-Jun	Be able to get results for an arbitrary timeseries with a regression
24-Apr	Introduction to financial data & the stock market (what, why, how does it work)				12-Jun	Calculate Error with RMSE
24-Apr	Different kinds of financial data, different kinds of markets (bullish/bearish, volatile/stable)				12-Jun	Allow selection of data load method (function / file)
24-Apr	Source of financial data				12-Jun	Build regression learner based on passed parameters		Could add additional options later
24-Apr	Typical analysis of financial data				12-Jun	Give regression learner specified training data
	Prediction Pseudo Code				12-Jun	Test regression learner with specified testing data
	Pre-Processing (link with financial data analysis)				12-Jun	Allow selection of error calculation method & calculate training and test error
	Compare results to reference paper & visualize		Documented results (console output) for henon map		19-Jun	Test results for the Henon map
	Compare results with actual financial data & visualize (For each (supposed) improvement separately)				12.07	Check why Henon map results for higher levels don’t get more accurate		Forgot to set solver accuracy, works now
					12.07	Add preconditioning		Seems to be implemented (using the identity matrix)
					12.07	Add adaptivity
					12.07	Test results for Jump Map, ANN & CI Forecasting Competition 2006/2007		Results are a bit less accurate for testing, than the comparison paper. Need to take another look at the data scaling. It is possible that not using the same rescaling for training & test data is the cause
					19-Jun	Testing system
					19-Jun	Financial Data pipeline
						Test non-adaptive system for all markets combined
						Test non-adaptive system for different markets
						Test adaptive system for all markets combined
						Test adaptive system for different markets
						Pre Processing of finance data
						Test adaptive system w/ preprocessing for all markets combined
						Test adaptive system w/ preprocessing for different markets
						Other improvements