## Tabelle1
		Legend				Legend
		not started				Done this week	not started
		started					started
		done					done

Writing					Implementation
Date	Milestone	Progress	Comments		Date	Milestone	Progress	Comments
	Abstract				15-May	Install pysgpp & virtual box
29-May	Introduction to SG				15-May	Pysgpp tutorial
29-May	Derive SG Formula		Needs to be fleshed out with description, just a rough derivation sketch so far		5-Jun	File parser
	Link regular SG to timeseries prediction				12-Jun	Rescale data to sg interval
	Comparable procedures				12-Jun	Be able to get results for an arbitrary timeseries with a regression
24-Apr	Introduction to financial data & the stock market (what, why, how does it work)				12-Jun	Calculate Error with RMSE
24-Apr	Different kinds of financial data, different kinds of markets (bullish/bearish, volatile/stable)				12-Jun	Allow selection of data load method (function / file)
24-Apr	Source of financial data				12-Jun	Build regression learner based on passed parameters		Could add additional options later
24-Apr	Typical analysis of financial data				12-Jun	Give regression learner specified training data
	Prediction Pseudo Code				12-Jun	Test regression learner with specified testing data
	Pre-Processing (link with financial data analysis)				12-Jun	Allow selection of error calculation method & calculate training and test error
	Compare results to reference paper & visualize		Documented results (console output) for henon map		19-Jun	Test results for the Henon map
	Compare results with actual financial data & visualize (For each (supposed) improvement separately)				12.07	Check why Henon map results for higher levels don’t get more accurate		Forgot to set solver accuracy, works now
25.07.	Added proposal for detailed outline				12.07	Add preconditioning		Seems to be implemented (using the identity matrix), change this to preconditioning used in reference paper?
					25.07.	Add adaptivity		Started on this, doesn’t seem to do anything when specifying a threshold, it does work when specifying a specific number of points to adapt.
					18.07.	Test results for Jump Map, ANN & CI Forecasting Competition 2006/2007		Results are a bit less accurate for testing, than the comparison paper. Add adaptivity-tests
					19-Jun	Testing system
					25.07.	Financial Data pipeline		Started on this. Can specify with/w.o. adaptivity, how many testing vectors should be built & how many steps should be predicted for each test vector. Next steps, automatically get all market data and run test for all.		Could build separate pipeline, since the methods and settings for financial data are much more specific than the ones for the reference tests
						Test non-adaptive system for all markets combined
						Test non-adaptive system for different markets
						Test adaptive system for all markets combined
						Test adaptive system for different markets
					25.07.	Pre Processing of finance data		Add suitable prediction market identification (test for different market types, see if prediction is more applicable to some – if yes -> add identification as preprocessing. If no →no need for identification)
						Test adaptive system w/ preprocessing for all markets combined
						Test adaptive system w/ preprocessing for different markets
						Other improvements
					18.07.	Visualization		Need to close window before next one is drawn. Could automate this with screenshots etc.
					25.07.	Added dimensionality estimation with Grassberger algorithm		Nolds module. Need to specify max embedding dimension. Testing for 1-100 and using rounded max value.